| ZIMBABWE NATIONAL GEOSPATIAL AND SPACE AGENCY ZINGSA 630 Churchill Avenue, Mount Pleasant, Harare ¦ +263 868 800 3466 ¦ publicrelations@zingsa.ac.zw |  |  |  |
| --- | --- | --- | --- |

COMBINED TECHNICAL & FINANCIAL PROPOSAL National Irrigation Geospatial Database System Mobile Application · WebGIS Dashboard · Hosting · Training · Support

| Submitted To: | Ministry of Lands, Agriculture, Water, Climate & Rural Resettlement |
| --- | --- |
| Submitted By: | Zimbabwe National Geospatial and Space Agency (ZINGSA) |
| Proposal Ref: | ZINGSA/MLAWCRR/NIGD/2026/001 |
| Date: | 9 July 2026 |
| Total Proposal Value: | USD $47,800.00 |

| TOC | TABLE OF CONTENTS |
| --- | --- |

| 1 | Executive Summary |
| --- | --- |
| 2 | About ZINGSA |
| 3 | Understanding of the Project |
| 4 | Technical Approach & Methodology |
| 5 | System Architecture |
| 6 | Key Deliverables |
| 7 | Implementation Timeline |
| 8 | Project Team & Qualifications |
| 9 | Financial Proposal |
| 10 | Payment Schedule |
| 11 | Terms & Conditions |

| 1 | EXECUTIVE SUMMARY |
| --- | --- |

ZINGSA proposes a transformative digital solution to create Zimbabwe's first National Irrigation Geospatial Database — a centralized, data-driven platform for the collection, management, visualization, and analysis of irrigation infrastructure across all provinces of Zimbabwe.

The Zimbabwe National Geospatial and Space Agency (ZINGSA) is pleased to submit this combined Technical and Financial Proposal for the development of the National Irrigation Geospatial Database System (NIGD). This initiative responds directly to the concept note approved by the Chief Director, Water Resources & Irrigation Development, and the Director ICT, and aligns with Zimbabwe's Vision 2030 agenda of achieving an upper-middle-income economy through technology-driven agricultural transformation.

The proposed system will comprise four tightly integrated components:

| 📱 Mobile Application Field data collection with GPS tracking, offline capability, and photo capture. | 🌐 WebGIS Dashboard Interactive maps, analytics, reporting, and multi-user administration. |
| --- | --- |
| ☁️ Hosting & Infrastructure Cloud-based backend, PostgreSQL/PostGIS, SSL-secured, 12-month managed hosting. | 🎓 Training & Support Train-the-trainer sessions, end-user training, manuals, and 12-month post-go-live support. |

The total investment for this solution is USD $47,800.00, covering full system development, deployment, one year of hosting, comprehensive training, and first-year post-delivery support. ZINGSA brings proven geospatial expertise, institutional credibility, and existing infrastructure to deliver this project on time and within budget.

| 2 | ABOUT ZINGSA |
| --- | --- |

| ZINGSA Zimbabwe National Geospatial & Space Agency | Headquarters: 630 Churchill Avenue, Mount Pleasant, Harare (Zimbabwe Science Park 1, University of Zimbabwe) Phone: +263 868 800 3466 / +263 867 700 9885 Email: publicrelations@zingsa.ac.zw Mandate: National geospatial data infrastructure, satellite technologies & GIS solutions |
| --- | --- |

ZINGSA is Zimbabwe's premier geospatial institution, established to advance the country's geospatial data infrastructure through cutting-edge satellite and GIS technologies. The agency has successfully delivered digital transformation projects across multiple government ministries, providing mapping, spatial analysis, web application development, and mobile GIS solutions.

Why ZINGSA?

✔  Geospatial Expertise: Deep in-house capability in GIS, remote sensing, satellite data processing, and geospatial software development — the exact skillset this project demands.

✔  Government Partnership: As a government agency, ZINGSA understands ministry workflows, data governance requirements, and public-sector ICT compliance standards.

✔  Proven Track Record: ZINGSA has developed and deployed web and mobile GIS applications for national infrastructure monitoring and mapping programmes.

✔  Technology Stack Alignment: ZINGSA's existing platforms use Django, PostGIS, GeoServer, and Leaflet.js — the same stack proposed for this system — ensuring zero learning curve.

✔  Data Sovereignty: Hosting within Zimbabwe's national infrastructure ensures data sovereignty, security, and compliance with national data protection frameworks.

| 3 | UNDERSTANDING OF THE PROJECT |
| --- | --- |

ZINGSA has carefully reviewed the National Irrigation Geospatial Database concept note approved by senior Ministry officials. We understand that the Ministry requires a modern, scalable digital system to address critical gaps in irrigation data management across Zimbabwe.

The Problem

Irrigation data is fragmented across provinces with no centralized repository.

Monitoring of irrigation infrastructure is largely manual, slow, and inaccurate.

There is no geospatial visualization of irrigation schemes at national scale.

Early warning for irrigation-related hazards (floods, droughts, frost) lacks data infrastructure.

Policy formulation suffers from delayed, incomplete, and non-spatial data.

The Proposed Solution

ZINGSA proposes the National Irrigation Geospatial Database (NIGD) — an integrated digital platform that:

Collects irrigation data in the field via a GPS-enabled Android mobile application with offline capability.

Stores all data centrally in a PostgreSQL/PostGIS spatial database for structured, queryable storage.

Visualizes irrigation schemes on an interactive WebGIS map dashboard accessible from any browser.

Enables real-time monitoring of infrastructure status, maintenance needs, and performance metrics.

Integrates satellite and remote sensing data for predictive early warning and yield forecasting.

Supports multi-stakeholder data sharing across ministries, research institutions, and development partners.

Aligns with Zimbabwe Vision 2030 and national food security objectives.

Alignment with National Priorities

| National Framework | Relevant Target | NIGD Contribution |
| --- | --- | --- |
| Zimbabwe Vision 2030 | Upper-middle income through agriculture | Digital irrigation monitoring & reporting |
| National Water Policy | Efficient water resource management | Real-time irrigation infrastructure tracking |
| Sustainable Dev. Goals | SDG 2 (Zero Hunger), SDG 6 (Clean Water) | Evidence-based irrigation investment decisions |

| 4 | TECHNICAL APPROACH & METHODOLOGY |
| --- | --- |

ZINGSA will follow an Agile delivery methodology with two-week sprints, ensuring continuous stakeholder feedback, rapid iteration, and transparent progress reporting throughout the project lifecycle.

4.1  Mobile Application (Android — Field Data Collection)

The mobile application will be the primary tool for field surveyors and irrigation officers to capture real-time data from irrigation schemes across Zimbabwe.

| Feature | Description |
| --- | --- |
| GPS Data Capture | Automatic location tagging of irrigation schemes, canals, pumping stations, and boreholes. |
| Irrigation Form Wizard | Guided data entry forms for plot size, crop types, water source, infrastructure condition, and productivity levels. |
| Photo & Media Attachment | Field officers can attach photographs of infrastructure for visual condition assessment. |
| Offline-First Architecture | Full functionality without internet connectivity. Data is queued locally (SQLite) and auto-synced when connected. |
| Scheme Status Tracking | Field officers can update operational status, maintenance flags, and seasonal crop data per scheme. |
| User Authentication | Secure login tied to province/district assignments with role-based access. |
| Push Notifications | Real-time alerts to field teams for scheduled surveys, maintenance reminders, and hazard warnings. |

4.2  WebGIS Dashboard (Frontend Interface)

The WebGIS dashboard provides supervisors, policymakers, and administrators with a powerful browser-based platform to visualize, analyze, and export national irrigation data.

Interactive Leaflet.js map showing all irrigation schemes color-coded by status, crop type, or province.

Click-on-scheme popups displaying full attribute data, photos, and historical records.

Province/district/scheme drill-down navigation for multi-level data exploration.

Thematic mapping — toggle layers for water sources, crop coverage, infrastructure condition, and satellite imagery.

Dashboard analytics — irrigated area totals, scheme counts, operational ratios, and trend charts.

Search & filter panel — query schemes by type, crop, province, season, or status.

Data export — downloadable reports in CSV, Excel, PDF, and GeoJSON/Shapefile formats.

Early warning panel — flag drought zones, flood-prone schemes, and frost occurrence areas.

Admin panel — manage users, provinces, scheme registry, and system configuration.

Responsive design — accessible on desktops, tablets, and mobile browsers.

4.3  Backend & Database

The backend will be built on a robust, production-grade stack proven in geospatial applications:

| Component | Technology | Purpose |
| --- | --- | --- |
| Web Framework | Django + GeoDjango | Business logic, REST API, geospatial query engine |
| Database | PostgreSQL + PostGIS | Spatial data storage, indexing, and geospatial analytics |
| Geospatial API | GeoServer | Serve vector/raster layers, WMS/WFS tile services |
| Frontend Map | Leaflet.js + OpenLayers | Interactive map rendering in browser |
| Authentication | JWT / OAuth 2.0 | Secure session management and role-based access |

|  | SYSTEM ARCHITECTURE |
| --- | --- |

The NIGD system follows a three-tier architecture — Field Collection → Cloud Backend → Web Presentation — ensuring data flows seamlessly from irrigation officers in the field to decision-makers in Harare.

| FIELD LAYER |  | BACKEND LAYER |  | PRESENTATION LAYER |
| --- | --- | --- | --- | --- |
| 📱 Android Mobile App | ──► WiFi/4G | ⚙ Django REST API | ──► | 🌐 WebGIS Dashboard |
| GPS ¦ Forms Photos ¦ Offline |  | GeoDjango GeoServer WMS |  | Leaflet.js Maps Charts ¦ Reports |
| ▼ |  | ▼ |  | ▼ |
| 📦 SQLite (Offline Cache) |  | 🗄 PostgreSQL + PostGIS DB |  | 👥 Admin Panel User Management |
| ◄──── Auto Sync on Connectivity ────► |  |  |  |  |
| ☁ Cloud Hosting (SSL Secured) ¦ 🛰 Satellite / Remote Sensing Data Integration |  |  |  |  |

Figure 1: National Irrigation Geospatial Database — Three-Tier System Architecture

| 6 | KEY DELIVERABLES |
| --- | --- |

| Ref | Deliverable | Description |
| --- | --- | --- |
| D1 | Mobile Application (Android APK) | GPS-enabled field data collection app with offline sync, photo capture, and scheme status tracking. |
| D2 | WebGIS Dashboard | Browser-based interactive map with scheme visualization, analytics, reporting, and admin functions. |
| D3 | Backend API & Database | Django REST API, PostgreSQL/PostGIS database, GeoServer, and RESTful data exchange layer. |
| D4 | Hosting & Infrastructure | 12-month cloud hosting, SSL certificates, automated backups, and performance monitoring. |
| D5 | User Training | Two structured training sessions (admin + field users), training manuals, and digital materials. |
| D6 | First Year Support | 12 months of post-go-live technical support, bug fixes, minor enhancements, and system updates. |
| D7 | Documentation Package | System architecture document, user manual, API documentation, and data dictionary. |

| 7 | IMPLEMENTATION TIMELINE |
| --- | --- |

The project will be delivered over 14 weeks from the date of contract signing, structured into five clearly defined phases:

| Activity / Week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1: Inception & Requirements | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 2: Mobile App Development |  | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |
| Phase 3: WebGIS & Backend Dev. |  |  | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |
| Phase 4: Integration & UAT |  |  |  |  |  |  | ■ | ■ | ■ |  |  |  |  |  |
| Phase 5: Deployment & Go-Live |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |  |
| Phase 6: Training (Admin + Field) |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |
| Phase 7: Handover & Documentation |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |
| Phase 8: First Year Support Begins |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ |

Figure 2: NIGD Implementation Gantt Chart (14-Week Project Timeline)

| 8 | PROJECT TEAM & QUALIFICATIONS |
| --- | --- |

ZINGSA will deploy a dedicated, experienced team for this engagement:

| Role | Responsibilities | Qualifications |
| --- | --- | --- |
| Project Manager | Overall project coordination, stakeholder liaison, milestone tracking, and quality assurance. | PMP Certified ¦ 8+ years in government ICT projects |
| GIS & Geospatial Lead | System architecture, PostGIS database design, GeoServer configuration, and spatial analytics. | MSc GIS ¦ 10+ years geospatial development |
| Mobile Developer (Android) | Android application development using Kotlin, offline-first SQLite architecture, GPS integration. | BSc Computer Science ¦ 5+ years Android development |
| Backend Developer | Django/GeoDjango API development, RESTful endpoints, authentication, and database management. | BSc Software Engineering ¦ 6+ years Django/Python |
| Frontend Developer (WebGIS) | Leaflet.js WebGIS interface, dashboard charts, export functions, and responsive UI. | BSc IT ¦ 5+ years web development & GIS |
| GIS Data Analyst | Data validation, spatial analysis, schema design, and training content development. | BSc GIS & Remote Sensing ¦ 4+ years |
| Training Coordinator | User training design, session facilitation, manual production, and post-training assessment. | Education background + 3+ years GIS training |

| 9 | FINANCIAL PROPOSAL |
| --- | --- |

The following financial proposal is presented for the full design, development, deployment, training, hosting, and first-year support of the National Irrigation Geospatial Database System. All amounts are in United States Dollars (USD).

| # | Component | Scope / Description | Qty | Amount (USD) |
| --- | --- | --- | --- | --- |
| 1 | Mobile Application Development | Android mobile app (GPS, forms, photo, offline sync, user auth, push notifications) | 1 | USD $12,000.00 |
| 2 | WebGIS Dashboard & Backend | Django/GeoDjango REST API, PostGIS database, GeoServer, Leaflet.js frontend, admin panel, analytics | 1 | USD $14,500.00 |
| 3 | Server Configuration & Infrastructure | Cloud server setup, PostgreSQL/PostGIS installation, GeoServer, SSL certificates, CI/CD pipeline | 1 | USD $2,800.00 |
| 4 | Hosting (12 Months) | Managed cloud hosting, bandwidth, storage, automated backups, uptime monitoring — Year 1 | 12 months | USD $3,500.00 |
| 5 | User Training | 2 structured training sessions (administrators + field surveyors), manuals, digital resources | 2 sessions | USD $5,000.00 |
| 6 | First Year Support & Maintenance | 12 months of technical support, bug fixes, minor feature updates, performance tuning | 12 months | USD $5,500.00 |
| 7 | Contingency (10%) | Risk buffer for scope adjustments, travel, consumables, and unforeseen technical challenges | — | USD $4,500.00 |
|  | GRAND TOTAL |  |  | USD $47,800.00 |

Budget Distribution

| Component | Budget Bar | Amount |
| --- | --- | --- |
| Mobile Application | ██████████ 25.2% | $12,000 |
| WebGIS & Backend | ████████████ 30.3% | $14,500 |
| Server Config | ██ 5.9% | $2,800 |
| Hosting (12mo) | ██ 7.3% | $3,500 |
| Training | ████ 10.5% | $5,000 |
| First Year Support | ████ 11.5% | $5,500 |
| Contingency | ███ 9.4% | $4,500 |

Figure 3: Visual budget ditribution across project components:

| 10 | PAYMENT SCHEDULE |
| --- | --- |

Payments shall be tied to verified project milestones. All invoices are payable within thirty (30) calendar days of submission.

| Milestone | Description | % | Amount (USD) | Target |
| --- | --- | --- | --- | --- |
| Milestone 1 | Contract Signing & Project Commencement | 30% | USD $14,340.00 | Week 1 |
| Milestone 2 | Beta Delivery — Mobile App & WebGIS Dashboard | 35% | USD $16,730.00 | Week 8 |
| Milestone 3 | Go-Live, Training Completion & Handover | 25% | USD $11,950.00 | Week 12 |
| Milestone 4 | End of First Year Support Period | 10% | USD $4,780.00 | Month 14 |
| TOTAL |  | 100% | USD $47,800.00 | — |

All payments to be made in USD to ZINGSA's designated bank account within 30 days of invoice. Invoice reference: ZINGSA/MLAWCRR/NIGD/2026/001

| 11 | TERMS & CONDITIONS |
| --- | --- |

▶  Validity of Proposal: This proposal is valid for ninety (90) days from the date of submission.

▶  Intellectual Property: Upon receipt of full payment, all intellectual property rights in the custom-developed software, documentation, and training materials shall vest in the Client.

▶  Warranty Period: ZINGSA provides a ninety (90) day post-delivery warranty covering defects attributable to workmanship. Issues arising from misuse or unauthorized modifications are excluded.

▶  First Year Support: First-year support covers technical bug fixes, minor feature updates, and system performance tuning for 12 months post-go-live. Major new features will be quoted separately.

▶  Confidentiality: Both parties agree to maintain the confidentiality of all project-related information and data accessed during the engagement.

▶  Hosting Renewal: Hosting services included in this proposal cover Year 1 only. Year 2+ hosting renewal shall be subject to a separate service agreement.

▶  Change Management: Any scope changes must be agreed in writing. ZINGSA will provide a change request estimate within 5 business days of receiving a written change request.

▶  Governing Law: This proposal and any resultant agreement shall be governed by and construed in accordance with the laws of Zimbabwe. Disputes shall be resolved through mediation or arbitration.

▶  Force Majeure: Neither party shall be liable for delays caused by circumstances beyond reasonable control, including acts of God, governmental actions, or telecommunications infrastructure failures.

ROPOSAL ACCEPTANCE & AUTHORISATION

Should the Ministry wish to proceed on the basis of this proposal, we request the authorised representative to sign and return this acceptance page, which shall initiate contract finalisation and project commencement.

| FOR AND ON BEHALF OF THE PROPOSER Zimbabwe National Geospatial and Space Agency (ZINGSA) Name: ___________________________ Title: Director General / Director, GIS Directorate Signature: ___________________________ Date: ___________________________ Official Stamp: | FOR AND ON BEHALF OF THE CLIENT Ministry of Lands, Agriculture, Water, Climate & Rural Resettlement Name: ___________________________ Title: Permanent Secretary / Authorised Representative Signature: ___________________________ Date: ___________________________ Official Stamp: |
| --- | --- |

ZINGSA | 630 Churchill Avenue, Mount Pleasant, Harare | +263 868 800 3466 | publicrelations@zingsa.ac.zw
Proposal Ref: ZINGSA/MLAWCRR/NIGD/2026/001 | Total Value: USD $47,800.00 | Date: 9 July 2026